CONSOLIDATED SUPPORT PACKAGE

HVAC relocation REA | Price and time substantiation

TO: Contracting Officer, 713th Contracting Squadron (713 CONS)

FROM: Outer Heaven Builders, LLC

DATE: 7 May 2027

CONTRACT: SM-SABER-01, Task Order 27-041

RELATED SUBMISSION: AB-01 dated 4 May 2027

REQUESTED ADJUSTMENT $280,000 ¦ 14 calendar days ¦ Revised completion: 29 September 2027

# Proposal basis

This package consolidates the price, quantity, salvage, mitigation, and schedule records supporting Outer Heaven's AB-01 request. Civil Engineering determined that the awarded straight HVAC route and the separately awarded stage configuration could not coexist. The priced correction removes only affected installed work, preserves unaffected work, and reroutes the HVAC distribution around the western stage clearance zone.

| Zanzibar Mechanical net subcontract quotation | $208,000 |
| --- | --- |
| Extended field supervision / SSHO / quality control | $30,800 |
| Site logistics and access-equipment coordination | $11,200 |
| Prime home-office overhead | $12,000 |
| Bond and insurance adjustment | $4,000 |
| Prime profit | $14,000 |
| TOTAL REQUESTED PRICE ADJUSTMENT | $280,000 |

# Reconciliation

The subcontract quotation is net of $28,200 in salvage, reuse, and avoided-work credits. Prime costs are limited to the added 14-day critical period and the incremental administration of the correction. No original-scope amount, previously reimbursed cost, or cost claimed under another request is included.

SUBCONTRACTOR QUOTATION

Zanzibar Mechanical Services, LLC | Quotation ZMS-27-118-R2

QUOTE DATE: 6 May 2027

VALIDITY: 30 calendar days

BASIS: B-03 installed route; field quantities through 3 May; Government-requested perimeter correction

| ITEM | WORK ELEMENT | QTY / UNIT | AMOUNT |
| --- | --- | --- | --- |
| 01 | Field verification, coordination, and revised shop drawings | 240 HR | $18,500 |
| 02 | Protection and selective demolition of conflicting installed runs | 1 LS | $31,800 |
| 03 | Replacement insulated canvas duct, fittings, and supports | 730 LF | $86,400 |
| 04 | Replacement control conduit, junctions, and conductors | 510 LF | $34,600 |
| 05 | Reinstallation labor, lifts, and access equipment | 18 SHIFT | $52,300 |
| 06 | Testing, adjusting, balancing, controls checkout, and startup | 11 ZONE | $12,600 |
|  | GROSS ADDED WORK |  | $236,200 |
| CR-1 | Salvage and reuse credit | SEE BELOW | ($18,700) |
| CR-2 | Avoided original-scope work credit | SEE BELOW | ($9,500) |
|  | NET SUBCONTRACT QUOTATION |  | $208,000 |

# Segregated quantity and credit record

| Affected installed work | 560 LF canvas duct; 410 LF control conduit; 64 hangers; 8 diffusers |
| --- | --- |
| Retained in place | All eastern equipment, main trunk, room branches, and utility-room work outside the conflict zone |
| Salvaged for reuse | 210 LF duct sections; 64 hangers; 8 diffusers; 310 LF conductors; reusable controls hardware |
| Avoided work | Uninstalled western takeoffs and finish work deleted from the original straight-route sequence |
| Cost segregation | ZMS cost codes 27-041-R2-01 through -06; separate timecards, delivery tickets, and equipment logs |

Price-book check: standard work elements were reconciled to the fictional localized UPG-FY27-SM-AK and the awarded SM-SABER-01 coefficients. Non-price-book coordination and integration were supported by the hours and quantities above.

MITIGATION & SCHEDULE

Contemporaneous record and 14-day critical-path fragnet

# Mitigation actions

| 3 May | Stopped only the western conflict-zone work; protected completed eastern and side-room work. |
| --- | --- |
| 3-4 May | Field-verified a perimeter route and reused supports, diffusers, conductors, and accessible duct sections. |
| 4 May | Reserved local lift equipment and combined demolition with fabrication to avoid a second mobilization. |
| 5 May | Authorized expedited fabrication within the quoted price; avoided six additional calendar days. |
| Daily | Maintained separate R2 cost codes and resequenced unaffected closeout work where access permitted. |

# Schedule fragnet

| ID | ACTIVITY | DUR. | CHANGE DAY | LOGIC |
| --- | --- | --- | --- | --- |
| R2-10 | Field verification / final route | 2 | 1–2 | Critical start |
| R2-20 | Fabricate replacement duct and controls | 4 | 3–6 | Follows R2-10 |
| R2-25 | Selective demolition and salvage | 3 | 3–5 | Concurrent with fabrication |
| R2-30 | Install rerouted duct and conduit | 5 | 7–11 | Follows R2-20 and R2-25 |
| R2-40 | TAB, controls checkout, startup | 2 | 12–13 | Follows R2-30 |
| R2-50 | Closeout / release stage workfront | 1 | 14 | Follows R2-40 |

| Controlling effect | Stage upper-frame work cannot begin until R2-50 releases the shared western workfront. |
| --- | --- |
| Net extension | 14 calendar days; 15 September 2027 moves to 29 September 2027. |
| Concurrency | No overlapping contractor-caused critical delay appears in the 3-16 May schedule updates or daily reports. |
| Further mitigation | Additional acceleration would require premium labor and would not reduce fabrication below the reserved four-day cycle. |

CONTRACTOR STATEMENT. To the best of our knowledge, this package contains only allocable, unreimbursed costs and time effects arising from the described HVAC relocation. Supporting timecards, invoices, delivery tickets, daily reports, and electronic schedule files are available for audit or fact-finding.

/s/ Robin Hale
Project Manager, Outer Heaven Builders, LLC  |  7 May 2027

APPENDIX A — REVISED HVAC ROUTE