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PROPOSED SABER TASK ORDER AWARD SUMMARY
Runway 10/28 approach-light restoration
	Requirement
	AF-27-014 | Runway 10/28 approach-light restoration

	Proposed order
	SM-SABER-01 | Task Order 27-052 | Firm-fixed-price

	Prime / disclosed sub
	Outer Heaven Builders, LLC / Northern Beacon Electric, LLC

	Value / funds
	$7,350,000 | FY24 Military Construction, Air Force (3300)

	Performance
	Interim operating configuration: NTP + 10 days | Complete: NTP + 20 days

	Liquidated damages
	$8,500 per calendar day under FAR 52.211-12


Requirement and proposed award
A series of irregular hailstorms during 2026 broke nearly all approach lights serving Runway 10/28. Airfield Operations (713 AOS) requires urgent restoration before the next severe-weather season. Work includes light assemblies, foundations, cabling, transformers, control interfaces, testing, and an interim operating configuration. Because timely performance is exceptionally important and the probable operational harm from delay is difficult to quantify precisely, the proposed order includes the FAR 52.211-12 rate shown above. The construction limits are inside the controlled flightline. No award or notice to proceed has been issued.
Award-package inventory
	Award-package element
	File status

	Scope, 30% design, and phased restoration plan
	Included / technically approved

	Certified funding request and project-authority review
	Included / complete

	Government estimate, SABER coefficients, and price analysis
	Included / complete

	Wage determination, clauses, bonding, and insurance requirements
	Included / complete

	Safety, environmental, and operational phasing coordination
	Included / complete

	Prime/subcontractor roster and installation-entry sponsorship
	Approved - base access

	Proposed task order and award memorandum
	Prepared for CO decision



	ACCESS RECORD IN THIS PACKAGE. Security Forces (713 SFS) approved the named personnel for installation entry and all nonrestricted base locations through 30 September 2027. The work site lies beyond the controlled flightline gate. Airfield Operations (713 AOS), with Security Forces, administers the separate work-area authorization, restricted-area endorsement, and vehicle or pedestrian permissions used inside that boundary.


REVIEW STATUS: The proposed order is otherwise prepared for the Contracting Officer's award decision.
Prepared by: Amelie Emmerich, Contract Specialist, 713 CONS
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