DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

AGREED PROGRESS SCHEDULE & SCHEDULE OF VALUES

Task Order FA-27-005 - Payment Request No. 005

| Task-order value | $26,400,000.00 firm-fixed price |
| --- | --- |
| Notice to proceed | 22 March 2027 |
| Schedule status | Accepted for progress-payment administration on 18 March 2027 |
| Current period | 1 through 20 August 2027 |
| Payment status | $6,350,000.00 previously approved; $4,880,000.00 requested now |

# Complete payment breakdown

| SOV | Work portion | Scheduled value | Prior | Current | This request |
| --- | --- | --- | --- | --- | --- |
| 01 | Design completion, phasing, submittals | $1,850,000 | 90% | 100% | $185,000 |
| 02 | Mobilization, temporary facilities and protection | $1,100,000 | 80% | 85% | $55,000 |
| 03 | Selective demolition and hazardous-material controls | $2,100,000 | 60% | 60% | $0 |
| 04 | Structural renewal | $2,400,000 | 20% | 40% | $480,000 |
| 05 | Roofing renewal | $1,450,000 | 10% | 30% | $290,000 |
| 06 | Exterior-envelope renewal | $1,550,000 | 0% | 20% | $310,000 |
| 07 | Site and civil work | $750,000 | 0% | 20% | $150,000 |
| 08 | Electrical systems - installation plus staged permanent materials/equipment | $3,200,000 | 35% | 65% | $960,000 |
| 09 | HVAC systems - installation plus staged permanent equipment/materials | $4,000,000 | 20% | 60% | $1,600,000 |
| 10 | Fire protection, backup power and pathways | $1,200,000 | 0% | 20% | $240,000 |
| 11 | Drywall assemblies - installation plus staged materials | $1,600,000 | 0% | 25% | $400,000 |
| 12 | Interior finishes, ceilings, doors and fixtures | $2,200,000 | 0% | 0% | $0 |
| 13 | Security integration and mission systems | $2,100,000 | 0% | 10% | $210,000 |
| 14 | Testing, training and closeout | $900,000 | 0% | 0% | $0 |
|  | TOTAL | $26,400,000 | 24.05% | 42.54% | $4,880,000 |

ARITHMETIC CHECK: $11.23M cumulative earned value less $6.35M in prior approved payments equals the $4.88M current request.

| Accepted for payment administration | Signature / date |
| --- | --- |
| Maj Emma Emmerich, Contracting Officer, 713 CONS | /s/ Emma Emmerich - 18 Mar 2027 |
| Hot Coldman, President, Peace Walker Infrastructure Partners | /s/ Hot Coldman - 18 Mar 2027 |

CURRENT EARNED-VALUE SUPPORT

Installed work and delivered material - Payment Request No. 005

The accepted schedule separately weights physical installation and August delivery-and-staging milestones for permanent materials and equipment incorporated into the project. Payment Request No. 005 claims exactly those scheduled amounts.

# Progress-payment history

| Request | Period ending | Submitted | Approved | Net payment | Cumulative |
| --- | --- | --- | --- | --- | --- |
| 001 | 30 Apr 2027 | 3 May | 10 May | $1,750,000 | $1,750,000 |
| 002 | 31 May 2027 | 2 Jun | 9 Jun | $1,600,000 | $3,350,000 |
| 003 | 30 Jun 2027 | 2 Jul | 9 Jul | $1,450,000 | $4,800,000 |
| 004 | 31 Jul 2027 | 2 Aug | 9 Aug | $1,550,000 | $6,350,000 |
| 005 | 20 Aug 2027 | 24 Aug | PENDING | $4,880,000 | $11,230,000 |

# Accepted August milestones

| Schedule milestone | August plan | Achieved | Requested this month |
| --- | --- | --- | --- |
| Electrical installation | 17% / $544,000 | 17% / $544,000 | $544,000 |
| Electrical permanent materials/equipment staging | 13% / $416,000 | 13% / $416,000 | $416,000 |
| HVAC installation | 10% / $400,000 | 10% / $400,000 | $400,000 |
| HVAC permanent equipment/material staging | 30% / $1,200,000 | 30% / $1,200,000 | $1,200,000 |
| Drywall material staging | 25% / $400,000 | 25% / $400,000 | $400,000 |
| OTHER SOV 01-07, 10 and 13 MILESTONES | $1,920,000 | $1,920,000 | $1,920,000 |
| TOTAL CURRENT REQUEST | $4,880,000 | $4,880,000 | $4,880,000 |

# Delivered-material and permanent-equipment register

| Work | Material staged for this order | Delivery / location | Schedule credit |
| --- | --- | --- | --- |
| Electrical | Switchgear panels, feeders, cable reels and devices | ER-219; 16 Aug; secured east laydown | $416,000 / 13% |
| HVAC | Air handlers, duct sections, controls and supports | MR-441; 17 Aug; weatherproof mechanical staging | $1,200,000 / 30% |
| Drywall | Gypsum board, metal framing and accessories | IR-308; 18 Aug; enclosed Building 412 storage | $400,000 / 25% |

MATERIAL-CREDIT RECORD: The 18 March accepted schedule authorizes the stated August weights for permanent material and equipment delivered on site. Receiving tickets, paid supplier invoices, joint inventory sheets, contract-use identification, and protected-storage records are maintained in the contractor file. The listed items have not been included in a prior payment, and the requested staging credit exactly matches the accepted schedule.

CONTRACTOR: /s/ Mistral - Project Controller - Peace Walker Infrastructure Partners, LLC - 24 Aug 2027

JOINT INVENTORY: /s/ Meryl Silverburgh - Construction Inspector - 713 CES - 21 Aug 2027