DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

LIMITED SAFETY STOP-WORK MEMORANDUM

Campbell Hall | Task Order FA-27-005

MEMORANDUM FOR: Peace Walker Infrastructure Partners, LLC

FROM: Maj Emma Emmerich, Contracting Officer, 713th Contracting Squadron

DATE / TIME: 7 July 2027 | 1215 Alaska time

SUBJECT: Immediate limited stop of wall-disturbing work; continue safe unaffected work

- Immediately stop cutting, drilling, sanding, opening, demolishing, or removing Campbell Hall interior wall assemblies in the affected zones. Maintain barricades, negative-access controls, warning signs, and preservation of the exposed condition.

- Continue work that the approved competent persons determine does not disturb affected materials, including safe exterior/site work, roof and envelope work, design and submittal activity, procurement, and other separately controlled tasks. Coordinate daily with the COR and Site Safety and Health Officer.

- Provide an updated work-zone map, abatement approach, segregated cost record, schedule-impact analysis, and resequencing proposal. Do not perform additional or changed work unless authorized in writing by the Contracting Officer.

- This memorandum preserves safety and evidence while the Government evaluates FAR 52.236-2. It does not resolve entitlement, price, time, or funding and is not authorization to exceed the task-order amount.

REQUIRED ACKNOWLEDGEMENT. Acknowledge receipt immediately and identify the superintendent, SSHO, and industrial-hygiene lead responsible for maintaining the limited stop.

/s/ EMMA EMMERICH
Major, USAF | Contracting Officer, 713 CONS
7 July 2027