DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

PRELIMINARY FUNDING-INCREASE ESTIMATE

Campbell Hall expanded asbestos response | Planning record as of 12 July 2027

| Task order | FA-27-005 ¦ Peace Walker Infrastructure Partners, LLC ¦ $26.40M FFP |
| --- | --- |
| Condition | 19 of 20 representative interior wall systems contain concealed ACM |
| Status | Government planning range only; no contractor proposal, negotiated amount, or certified additional funds |

# Preliminary upward-obligation range

| Planning component | Low | Working | High |
| --- | --- | --- | --- |
| Expanded containment, removal, disposal, and monitoring | $1.25M | $1.50M | $1.75M |
| Temporary protection, access, and occupied-building controls | $0.20M | $0.25M | $0.30M |
| Wall restoration and systems rework attributable to abatement | $0.45M | $0.55M | $0.65M |
| Time-related field overhead and schedule support | $0.30M | $0.30M | $0.30M |
| TOTAL PLANNING RANGE | $2.20M | $2.60M | $3.00M |

# Earliest projected approval sequence

| Milestone | Planning date | Dependency |
| --- | --- | --- |
| Contractor segregated proposal / schedule analysis | 14 Jul 2027 | Complete quantities, mitigation, and critical-path record |
| Government technical, price, scope, legal, and fiscal review | 18-20 Jul 2027 | Validated quantities, IGCE, entitlement, authority, and negotiation objective |
| Earliest additional certification and modification | 22 Jul 2027 | Approved funding action, Finance certification, and signed agreement |
| Targeted abatement and clearance | 23 Jul-5 Aug 2027 | Qualified crews, regulated areas, monitoring, and clearance results |

PLANNING USE ONLY. The estimate and dates create no entitlement or work authority. Any adjustment still requires validation, a fair-and-reasonable determination, certified funds, and a written Contracting Officer modification.

/s/ ROSEMARY MARQUEZ | Capt, USAF | Financial Management Officer, 713 CPTS | 12 July 2027