EXERCISE USE ONLY
COMMAND POST DESIGN-BUILD PROPOSAL
Diamond Dogs Civil Works, LLC | CP-27-008 | Submitted 21 July 2027
	OFFEROR STATEMENT. Mission resilience through an integrated secure-operations design


	Firm-fixed price
	$8,615,000

	Calendar duration
	410 days from notice to proceed

	Proposed turnover
	29 September 2028 · 16 days before required date

	Proposal validity
	120 calendar days

	Design responsibility
	Complete post-award design and construction by the design-builder

	Boulder stand-off
	North 62 ft · East 74 ft · South 58 ft · West 36 ft from the corresponding exterior wall


Executive approach
Diamond Dogs Civil Works, LLC offers one integrated design-build team for Building 100. The concept addresses 24/7 operations, secure communications, cold-region envelope performance, resilient utilities, controlled access, and fixed site-security barriers while retaining the existing footprint. Its boulder perimeter is 62 feet north, 74 feet east, 58 feet south, and 36 feet west of the corresponding exterior walls.
Response to stated evaluation factors
	Factor
	Offeror response

	Technical approach
	Exceptional. Central operations floor; secure rooms along the east service spine; public entry south; controlled service entry east. Two energy-recovery air handlers and three 50-percent hydronic boilers provide maintainable redundancy. Sectionalized distribution, a 150 kVA UPS, and two 300 kW generators support continuous operations.

	Management approach
	Very Good. One accountable manager; integrated submittal register; weekly discipline coordination; quality-control and safety gates.

	Schedule
	Very Good. 410 days; turnover 29 September 2028; 16 days of stated contingency.

	Key personnel
	Dedicated program manager, design manager, and superintendent identified below.

	Past performance
	Three comparable records supplied with quality, timeliness, and cost-control context.

	Price
	Firm-fixed price of $8,615,000 for complete design, construction, commissioning, training, and closeout.


Principal strengths
Most resilient mechanical and electrical concept.
One-model design-management plan with weekly discipline clash reviews.
Strongest key-personnel depth and most relevant secure-facility record.
CONCEPT DESIGN
Offeror-developed floor, systems, and security layout · not construction documents
[image: ]
	DESIGN STATUS. This is a concept-level submission. Final dimensions, calculations, grading, utilities, foundations, anchorage, and construction details will be developed after award through the required design reviews.


MANAGEMENT AND SCHEDULE
Design-construction integration and proposed control plan
Management approach
One program manager controls price, schedule, design, construction, subcontracts, and Government correspondence.
A common design model, submittal register, and weekly meeting link architectural, structural, civil, mechanical, electrical, communications, security, fire, and commissioning disciplines.
Preparatory, initial, and follow-up quality-control phases precede each definable feature; safety planning and activity-hazard analysis are integrated into release decisions.
Long-lead equipment is released after accepted design information; field verification precedes demolition and fabrication.
Key personnel
	Individual
	Role and qualifications

	Dana Rourke, PE
	Program Manager · 14 years remote vertical construction

	Samuel Hideo, AIA
	Design Manager · 11 secure operations facilities

	Marcus Flint
	Superintendent · 9 Alaska projects without lost-time injury


Proposed schedule
	Milestone
	Date / period
	Control

	Notice to proceed
	16 Aug 2027
	Baseline and field verification begin.

	35% design
	22 Sep 2027
	Confirm floor, site, systems, and long-lead basis.

	65% design
	20 Nov 2027
	Resolve coordination before broad construction release.

	95% design
	19 Jan 2028
	Complete systems and commissioning requirements.

	Final design
	16 Feb 2028
	Issue accepted construction package.

	Construction
	Oct 2027 – Aug 2028
	Envelope, interiors, systems, security, and sitework.

	Commission / train
	Aug – Sep 2028
	Testing, training, punch list, and closeout.

	Offeror turnover
	29 September 2028
	16 days before 15 Oct 2028.


PAST PERFORMANCE AND PRICE
Quality, timeliness, cost control, and firm-fixed-price offer
Relevant record
	Project
	Value
	Quality
	Timeliness
	Cost control

	North Radar Support Facility
	$7.40M
	Very Good
	12 days early
	Good; 0.8% Government-change growth

	Fort Raven Secure Operations Center
	$9.20M
	Exceptional
	On time
	Exceptional; absorbed coordination rework

	SM-MACC-01 Generator Annex
	$5.85M
	Very Good
	6 days early
	Very Good; 0.4% growth


The Government may verify the records above and consider relevance, context, and trend. All project names and performance records in this exercise proposal are fictional.
Firm-fixed-price breakout
	Item
	Price element
	Amount

	1
	Design, surveys, management, bonds, and controls
	$905,000

	2
	Roof and exterior envelope
	$1,465,000

	3
	Interior renewal and mission spaces
	$1,766,000

	4
	Electrical, emergency power, and communications pathways
	$1,465,000

	5
	HVAC, plumbing, fire protection, and life safety
	$905,000

	6
	Site security, boulders, entries, drainage, and restoration
	$862,000

	7
	Commissioning, training, closeout, and remote logistics
	$646,000

	8
	Offeror contingency and price balance
	$601,000

	
	TOTAL FIRM-FIXED PRICE
	$8,615,000


	OFFER. Diamond Dogs Civil Works, LLC offers the complete requirement for $8,615,000, firm fixed price, subject to SM-MACC-01 and CP-27-008.


AUTHORIZED OFFEROR: /s/ Dana Rourke, PE, for Diamond Dogs Civil Works, LLC
DATE: 21 July 2027
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