COMMAND POST DESIGN-BUILD PROPOSAL

Diamond Dogs Civil Works, LLC | CP-27-008 | Submitted 21 July 2027

OFFEROR STATEMENT. Mission resilience through an integrated secure-operations design

| Firm-fixed price | $8,615,000 |
| --- | --- |
| Calendar duration | 410 days from notice to proceed |
| Proposed turnover | 29 September 2028 · 16 days before required date |
| Proposal validity | 120 calendar days |
| Design responsibility | Complete post-award design and construction by the design-builder |
| Boulder stand-off | North 62 ft · East 74 ft · South 58 ft · West 36 ft from the corresponding exterior wall |

# Executive approach

Diamond Dogs Civil Works, LLC offers one integrated design-build team for Building 100. The concept addresses 24/7 operations, secure communications, cold-region envelope performance, resilient utilities, controlled access, and fixed site-security barriers while retaining the existing footprint. Its boulder perimeter is 62 feet north, 74 feet east, 58 feet south, and 36 feet west of the corresponding exterior walls.

# Response to stated evaluation factors

| Factor | Offeror response |
| --- | --- |
| Technical approach | Exceptional. Central operations floor; secure rooms along the east service spine; public entry south; controlled service entry east. Two energy-recovery air handlers and three 50-percent hydronic boilers provide maintainable redundancy. Sectionalized distribution, a 150 kVA UPS, and two 300 kW generators support continuous operations. |
| Management approach | Very Good. One accountable manager; integrated submittal register; weekly discipline coordination; quality-control and safety gates. |
| Schedule | Very Good. 410 days; turnover 29 September 2028; 16 days of stated contingency. |
| Key personnel | Dedicated program manager, design manager, and superintendent identified below. |
| Past performance | Three comparable records supplied with quality, timeliness, and cost-control context. |
| Price | Firm-fixed price of $8,615,000 for complete design, construction, commissioning, training, and closeout. |

# Principal strengths

Most resilient mechanical and electrical concept.

One-model design-management plan with weekly discipline clash reviews.

Strongest key-personnel depth and most relevant secure-facility record.

CONCEPT DESIGN

Offeror-developed floor, systems, and security layout · not construction documents

DESIGN STATUS. This is a concept-level submission. Final dimensions, calculations, grading, utilities, foundations, anchorage, and construction details will be developed after award through the required design reviews.

MANAGEMENT AND SCHEDULE

Design-construction integration and proposed control plan

# Management approach

One program manager controls price, schedule, design, construction, subcontracts, and Government correspondence.

A common design model, submittal register, and weekly meeting link architectural, structural, civil, mechanical, electrical, communications, security, fire, and commissioning disciplines.

Preparatory, initial, and follow-up quality-control phases precede each definable feature; safety planning and activity-hazard analysis are integrated into release decisions.

Long-lead equipment is released after accepted design information; field verification precedes demolition and fabrication.

# Key personnel

| Individual | Role and qualifications |
| --- | --- |
| Dana Rourke, PE | Program Manager · 14 years remote vertical construction |
| Samuel Hideo, AIA | Design Manager · 11 secure operations facilities |
| Marcus Flint | Superintendent · 9 Alaska projects without lost-time injury |

# Proposed schedule

| Milestone | Date / period | Control |
| --- | --- | --- |
| Notice to proceed | 16 Aug 2027 | Baseline and field verification begin. |
| 35% design | 22 Sep 2027 | Confirm floor, site, systems, and long-lead basis. |
| 65% design | 20 Nov 2027 | Resolve coordination before broad construction release. |
| 95% design | 19 Jan 2028 | Complete systems and commissioning requirements. |
| Final design | 16 Feb 2028 | Issue accepted construction package. |
| Construction | Oct 2027 – Aug 2028 | Envelope, interiors, systems, security, and sitework. |
| Commission / train | Aug – Sep 2028 | Testing, training, punch list, and closeout. |
| Offeror turnover | 29 September 2028 | 16 days before 15 Oct 2028. |

PAST PERFORMANCE AND PRICE

Quality, timeliness, cost control, and firm-fixed-price offer

# Relevant record

| Project | Value | Quality | Timeliness | Cost control |
| --- | --- | --- | --- | --- |
| North Radar Support Facility | $7.40M | Very Good | 12 days early | Good; 0.8% Government-change growth |
| Fort Raven Secure Operations Center | $9.20M | Exceptional | On time | Exceptional; absorbed coordination rework |
| SM-MACC-01 Generator Annex | $5.85M | Very Good | 6 days early | Very Good; 0.4% growth |

The Government may verify the records above and consider relevance, context, and trend. All project names and performance records in this exercise proposal are fictional.

# Firm-fixed-price breakout

| Item | Price element | Amount |
| --- | --- | --- |
| 1 | Design, surveys, management, bonds, and controls | $905,000 |
| 2 | Roof and exterior envelope | $1,465,000 |
| 3 | Interior renewal and mission spaces | $1,766,000 |
| 4 | Electrical, emergency power, and communications pathways | $1,465,000 |
| 5 | HVAC, plumbing, fire protection, and life safety | $905,000 |
| 6 | Site security, boulders, entries, drainage, and restoration | $862,000 |
| 7 | Commissioning, training, closeout, and remote logistics | $646,000 |
| 8 | Offeror contingency and price balance | $601,000 |
|  | TOTAL FIRM-FIXED PRICE | $8,615,000 |

OFFER. Diamond Dogs Civil Works, LLC offers the complete requirement for $8,615,000, firm fixed price, subject to SM-MACC-01 and CP-27-008.

AUTHORIZED OFFEROR: /s/ Dana Rourke, PE, for Diamond Dogs Civil Works, LLC

DATE: 21 July 2027