COMMAND POST DESIGN-BUILD PROPOSAL

Militaires Sans Frontières Construction JV | CP-27-008 | Submitted 21 July 2027

OFFEROR STATEMENT. Balanced cold-region performance with an accelerated exterior-work sequence

| Firm-fixed price | $8,340,000 |
| --- | --- |
| Calendar duration | 402 days from notice to proceed |
| Proposed turnover | 21 September 2028 · 24 days before required date |
| Proposal validity | 120 calendar days |
| Design responsibility | Complete post-award design and construction by the design-builder |
| Boulder stand-off | North 68 ft · East 78 ft · South 64 ft · West 40 ft from the corresponding exterior wall |

# Executive approach

Militaires Sans Frontières Construction JV offers one integrated design-build team for Building 100. The concept addresses 24/7 operations, secure communications, cold-region envelope performance, resilient utilities, controlled access, and fixed site-security barriers while retaining the existing footprint. Its boulder perimeter is 68 feet north, 78 feet east, 64 feet south, and 40 feet west of the corresponding exterior walls.

# Response to stated evaluation factors

| Factor | Offeror response |
| --- | --- |
| Technical approach | Very Good. Operations floor in the east half; command and briefing spaces in the west wing; public entry west; service entry south. Two 60-percent air handlers and two condensing boilers provide partial equipment redundancy. A sectionalized switchboard, 120 kVA UPS, and one 500 kW generator support priority loads. |
| Management approach | Very Good. One accountable manager; integrated submittal register; weekly discipline coordination; quality-control and safety gates. |
| Schedule | Very Good. 402 days; turnover 21 September 2028; 24 days of stated contingency. |
| Key personnel | Dedicated program manager, design manager, and superintendent identified below. |
| Past performance | Three comparable records supplied with quality, timeliness, and cost-control context. |
| Price | Firm-fixed price of $8,340,000 for complete design, construction, commissioning, training, and closeout. |

# Principal strengths

Strong envelope approach and credible remote logistics plan.

Price is $275,000 below the highest-priced offer.

Schedule retains 24 days before required turnover.

CONCEPT DESIGN

Offeror-developed floor, systems, and security layout · not construction documents

DESIGN STATUS. This is a concept-level submission. Final dimensions, calculations, grading, utilities, foundations, anchorage, and construction details will be developed after award through the required design reviews.

MANAGEMENT AND SCHEDULE

Design-construction integration and proposed control plan

# Management approach

One program manager controls price, schedule, design, construction, subcontracts, and Government correspondence.

A common design model, submittal register, and weekly meeting link architectural, structural, civil, mechanical, electrical, communications, security, fire, and commissioning disciplines.

Preparatory, initial, and follow-up quality-control phases precede each definable feature; safety planning and activity-hazard analysis are integrated into release decisions.

Long-lead equipment is released after accepted design information; field verification precedes demolition and fabrication.

# Key personnel

| Individual | Role and qualifications |
| --- | --- |
| Ana Valencia, CCM | Program Manager · 12 years occupied-facility renewal |
| Leonid Voronin, PE | Design Manager · cold-region envelope and mechanical specialist |
| Keith Webb | Superintendent · 8 years remote Alaska construction |

# Proposed schedule

| Milestone | Date / period | Control |
| --- | --- | --- |
| Notice to proceed | 16 Aug 2027 | Baseline and field verification begin. |
| 35% design | 22 Sep 2027 | Confirm floor, site, systems, and long-lead basis. |
| 65% design | 20 Nov 2027 | Resolve coordination before broad construction release. |
| 95% design | 19 Jan 2028 | Complete systems and commissioning requirements. |
| Final design | 16 Feb 2028 | Issue accepted construction package. |
| Construction | Oct 2027 – Aug 2028 | Envelope, interiors, systems, security, and sitework. |
| Commission / train | Aug – Sep 2028 | Testing, training, punch list, and closeout. |
| Offeror turnover | 21 September 2028 | 24 days before 15 Oct 2028. |

PAST PERFORMANCE AND PRICE

Quality, timeliness, cost control, and firm-fixed-price offer

# Relevant record

| Project | Value | Quality | Timeliness | Cost control |
| --- | --- | --- | --- | --- |
| Arctic Port Administration Renewal | $8.05M | Very Good | 18 days late | Good; weather recovery limited delay |
| SM-MACC-01 Medical Support Wing | $6.92M | Very Good | On time | Satisfactory; absorbed 2.8% rework |
| Tundra Watch Center Envelope | $4.30M | Very Good | 9 days early | Very Good; 0.6% growth |

The Government may verify the records above and consider relevance, context, and trend. All project names and performance records in this exercise proposal are fictional.

# Firm-fixed-price breakout

| Item | Price element | Amount |
| --- | --- | --- |
| 1 | Design, surveys, management, bonds, and controls | $876,000 |
| 2 | Roof and exterior envelope | $1,418,000 |
| 3 | Interior renewal and mission spaces | $1,710,000 |
| 4 | Electrical, emergency power, and communications pathways | $1,418,000 |
| 5 | HVAC, plumbing, fire protection, and life safety | $876,000 |
| 6 | Site security, boulders, entries, drainage, and restoration | $834,000 |
| 7 | Commissioning, training, closeout, and remote logistics | $626,000 |
| 8 | Offeror contingency and price balance | $582,000 |
|  | TOTAL FIRM-FIXED PRICE | $8,340,000 |

OFFER. Militaires Sans Frontières Construction JV offers the complete requirement for $8,340,000, firm fixed price, subject to SM-MACC-01 and CP-27-008.

AUTHORIZED OFFEROR: /s/ Ana Valencia, CCM, for Militaires Sans Frontières Construction JV

DATE: 21 July 2027