COMMAND POST DESIGN-BUILD PROPOSAL

Gray Fox Systems, Inc. | CP-27-008 | Submitted 21 July 2027

OFFEROR STATEMENT. A direct, economical renewal using commercially available systems

| Firm-fixed price | $7,990,000 |
| --- | --- |
| Calendar duration | 388 days from notice to proceed |
| Proposed turnover | 7 September 2028 · 38 days before required date |
| Proposal validity | 120 calendar days |
| Design responsibility | Complete post-award design and construction by the design-builder |
| Boulder stand-off | North 72 ft · East 82 ft · South 70 ft · West 44 ft from the corresponding exterior wall |

# Executive approach

Gray Fox Systems, Inc. offers one integrated design-build team for Building 100. The concept addresses 24/7 operations, secure communications, cold-region envelope performance, resilient utilities, controlled access, and fixed site-security barriers while retaining the existing footprint. Its boulder perimeter is 72 feet north, 82 feet east, 70 feet south, and 44 feet west of the corresponding exterior walls.

# Response to stated evaluation factors

| Factor | Offeror response |
| --- | --- |
| Technical approach | Acceptable. Operations floor in the north half; secure and support rooms in a south spine; public entry west; service entry south. Two packaged air handlers and two standard boilers use common components with limited redundancy. A single service spine, 100 kVA UPS, and one 500 kW generator support identified mission loads. |
| Management approach | Acceptable. One accountable manager; integrated submittal register; weekly discipline coordination; quality-control and safety gates. |
| Schedule | Very Good. 388 days; turnover 7 September 2028; 38 days of stated contingency. |
| Key personnel | Dedicated program manager, design manager, and superintendent identified below. |
| Past performance | Three comparable records supplied with quality, timeliness, and cost-control context. |
| Price | Firm-fixed price of $7,990,000 for complete design, construction, commissioning, training, and closeout. |

# Principal strengths

Lowest evaluated price and earliest turnover.

Commercial components simplify replacement-parts sourcing.

Simple phasing is easy to monitor.

CONCEPT DESIGN

Offeror-developed floor, systems, and security layout · not construction documents

DESIGN STATUS. This is a concept-level submission. Final dimensions, calculations, grading, utilities, foundations, anchorage, and construction details will be developed after award through the required design reviews.

MANAGEMENT AND SCHEDULE

Design-construction integration and proposed control plan

# Management approach

One program manager controls price, schedule, design, construction, subcontracts, and Government correspondence.

A common design model, submittal register, and weekly meeting link architectural, structural, civil, mechanical, electrical, communications, security, fire, and commissioning disciplines.

Preparatory, initial, and follow-up quality-control phases precede each definable feature; safety planning and activity-hazard analysis are integrated into release decisions.

Long-lead equipment is released after accepted design information; field verification precedes demolition and fabrication.

# Key personnel

| Individual | Role and qualifications |
| --- | --- |
| Naomi Hunter, PMP | Program Manager · 9 years federal renovation |
| Frank Jaeger, PE | Design Manager · commercial systems integration |
| George Kasler | Superintendent · 5 years remote construction |

# Proposed schedule

| Milestone | Date / period | Control |
| --- | --- | --- |
| Notice to proceed | 16 Aug 2027 | Baseline and field verification begin. |
| 35% design | 22 Sep 2027 | Confirm floor, site, systems, and long-lead basis. |
| 65% design | 20 Nov 2027 | Resolve coordination before broad construction release. |
| 95% design | 19 Jan 2028 | Complete systems and commissioning requirements. |
| Final design | 16 Feb 2028 | Issue accepted construction package. |
| Construction | Oct 2027 – Aug 2028 | Envelope, interiors, systems, security, and sitework. |
| Commission / train | Aug – Sep 2028 | Testing, training, punch list, and closeout. |
| Offeror turnover | 7 September 2028 | 38 days before 15 Oct 2028. |

PAST PERFORMANCE AND PRICE

Quality, timeliness, cost control, and firm-fixed-price offer

# Relevant record

| Project | Value | Quality | Timeliness | Cost control |
| --- | --- | --- | --- | --- |
| Fox Island Emergency Operations Center | $6.75M | Very Good | On time | Good; 1.1% growth |
| Remote Clinic Systems Renewal | $7.15M | Satisfactory | 33 days late | Marginal; 4.5% sequencing growth |
| SM-MACC-01 Warehouse Controls | $3.90M | Very Good | 7 days early | Very Good; no contractor growth |

The Government may verify the records above and consider relevance, context, and trend. All project names and performance records in this exercise proposal are fictional.

# Firm-fixed-price breakout

| Item | Price element | Amount |
| --- | --- | --- |
| 1 | Design, surveys, management, bonds, and controls | $839,000 |
| 2 | Roof and exterior envelope | $1,358,000 |
| 3 | Interior renewal and mission spaces | $1,638,000 |
| 4 | Electrical, emergency power, and communications pathways | $1,358,000 |
| 5 | HVAC, plumbing, fire protection, and life safety | $839,000 |
| 6 | Site security, boulders, entries, drainage, and restoration | $799,000 |
| 7 | Commissioning, training, closeout, and remote logistics | $599,000 |
| 8 | Offeror contingency and price balance | $560,000 |
|  | TOTAL FIRM-FIXED PRICE | $7,990,000 |

OFFER. Gray Fox Systems, Inc. offers the complete requirement for $7,990,000, firm fixed price, subject to SM-MACC-01 and CP-27-008.

AUTHORIZED OFFEROR: /s/ Naomi Hunter, PMP, for Gray Fox Systems, Inc.

DATE: 21 July 2027