FIRE-LANE PROCUREMENT + DELIVERY SCHEDULE

FL-27-014 | Baseline dated 20 July 2027

SCHEDULE PREMISE. The 31 August 2028 completion date supports Command Post commissioning. Coordination of the G and H site criteria is required before either acquisition creates contractor reliance.

| Milestone | Date | Status | Control / dependency |
| --- | --- | --- | --- |
| Requirement and certified funds | 10 Jul 2027 | Complete | H-01 through H-04 establish scope, funding, and fixed alignment. |
| Cross-project site review | 27 Jul 2027 | Decision point | Compare the Command Post proposals with this lane before either award. |
| Corrected common site criteria | 4 Aug 2027 | Planned | Issue any material correction through the applicable competition/order channel. |
| SABER proposal request | 9 Aug 2027 | Planned | Outer Heaven receives the coordinated H requirement. |
| Site verification and proposal | 12-30 Aug 2027 | Planned | Verify geometry, quantities, utilities, and remote logistics. |
| Negotiation and award | 1-15 Sep 2027 | Planned | Determine price fair and reasonable and issue the written task order. |
| Submittals and long-lead preparation | Sep 2027-Apr 2028 | Planned | Survey, geotechnical, aggregate, drainage, hydrant, and apparatus-turning submittals. |
| Earthwork and drainage | May-Jun 2028 | Planned | Thaw-sensitive work begins after accepted controls. |
| Aggregate, apron, and water work | Jul-Aug 2028 | Planned | Complete lifts, culverts, turning apron, lateral, hydrant, and restoration. |
| Apparatus test and final acceptance | 31 Aug 2028 | Required | Full-width access, turning, drainage, hydrant, and record-document verification. |

# Critical interface

A late relocation of installed Command Post boulders would consume winter-weather contingency, require demolition and reconstruction, and risk both the 31 August fire-lane completion and the 15 October Command Post turnover. The schedule contains time for pre-award proposal revision; it does not assume avoidable postaward relocation.

PREPARED BY: /s/ Hal Emmerich, NH-03, Chief Facilities Engineer, 713 CES

DATE: 20 July 2027