INDEPENDENT GOVERNMENT COST ESTIMATE

FL-27-014 | Command Post all-weather fire lane | 18 July 2027

| Estimate total | $4,160,000 |
| --- | --- |
| Pricing method | Localized SABER unit-price book quantities × awarded coefficient |
| Planned prime | Outer Heaven Builders, LLC |
| Water-work participant | Bering Fire & Water, LLC (planned subcontractor) |
| Price level | FY27 remote Alaska labor, material, equipment, and logistics basis |

METHOD. The Government did not invent lump-sum bid prices. It measured the H-02/H-03 work, extended localized public unit-price-book items, and applied Outer Heaven's awarded SABER coefficients. The resulting amount is an independent negotiation objective, not an entitlement.

| Item | Work element | Quantity | Book extension | Coeff. | Adjusted |
| --- | --- | --- | --- | --- | --- |
| 1 | Survey, design completion, management, bonds, controls | 1 LS | $410,000 | 0.970 | $397,700 |
| 2 | Clearing, excavation, grading, stabilization | 26,000 CY | $575,000 | 0.980 | $563,500 |
| 3 | Geotextile, aggregate lifts, compaction | 17,000 TON | $890,000 | 0.960 | $854,400 |
| 4 | Drainage ditches, culverts, erosion control | 1 LS | $490,000 | 0.990 | $485,100 |
| 5 | All-weather surface, shoulders, markers | 700 LF | $370,000 | 0.950 | $351,500 |
| 6 | Apparatus turning apron and tie-in | 1 LS | $520,000 | 0.980 | $509,600 |
| 7 | Hydrant lateral, valves, hydrant, testing | 1 LS | $610,000 | 0.990 | $603,900 |
| 8 | Mobilization, remote logistics, QA, closeout | 1 LS | $394,300 | 1.000 | $394,300 |
|  | TOTAL INDEPENDENT GOVERNMENT ESTIMATE |  |  |  | $4,160,000 |

# Estimate assumptions

Quantities reflect the fixed 700-linear-foot, 24-foot-clear alignment and turning apron in H-03; no security-boulder relocation is included.

Localized book extensions include ordinary crew labor, material, and equipment. Coefficients reflect the awarded SABER pricing relationship; the above-unit 1.000 logistics element recognizes remote mobilization without abandoning the coefficient method.

The estimate includes hydrant and lateral work, testing, quality control, winter protection needed for planned submittal activities, bonds, and closeout.

The estimate excludes Government-directed redesign or relocation caused by an unreconciled G/H interface, differing site conditions not disclosed in the current record, and postaward scope growth.

# Government approval

PREPARED: /s/ Decoy Octopus, GS-12, Cost Engineer, 713 CES

TECHNICAL REVIEW: /s/ Hal Emmerich, NH-03, Chief Facilities Engineer, 713 CES

DATE: 18 July 2027