DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

EXECUTED TASK ORDER FA-27-005

Campbell Hall Phased Headquarters Renovation

| Parent contract | SM-MACC-01 · Multiple-Award Construction Contract |
| --- | --- |
| Contractor | Peace Walker Infrastructure Partners, LLC |
| Order type / amount | Firm-fixed-price · $26,400,000.00 |
| Award / performance | Awarded 10 Mar 2027 · 22 Mar 2027 through 30 Sep 2028 |
| Place of performance | Campbell Hall, Shadow Moses Air Field, Alaska |
| Accounting | FY24 Military Construction, Air Force (3300) · fully obligated |

# Ordered work and price

| CLIN | Description | Amount |
| --- | --- | --- |
| 0001 | Design completion, phasing plan, and construction submittals | $1,850,000 |
| 0002 | Selective demolition, hazardous-material controls, and temporary protection | $3,200,000 |
| 0003 | Structural, roofing, exterior-envelope, and site renewal | $6,150,000 |
| 0004 | Electrical, mechanical, fire-protection, backup-power, and communications pathways | $8,400,000 |
| 0005 | Interior mission spaces, security integration, testing, training, and closeout | $6,800,000 |
|  | TOTAL FIRM-FIXED PRICE | $26,400,000 |

# Award and acceptance

The contractor shall furnish all design completion, labor, material, equipment, supervision, quality control, testing, and closeout required by this order and its incorporated scope, drawings, specifications, schedule, wage determination, and clauses. The order is effective on the award date; performance begins on the stated notice-to-proceed date.

| For the Government | For the contractor |
| --- | --- |
| /s/ Emma Emmerich Maj Emma Emmerich, USAF Contracting Officer, 713 CONS 10 Mar 2027 | /s/ Hot Coldman Hot Coldman President, Peace Walker Infrastructure Partners, LLC 10 Mar 2027 |

ORDER ADMINISTRATION SUMMARY

FA-27-005 · controlling task-order information

# Performance requirements

- Maintain the approved occupied-building phasing plan, safe egress, temporary utilities, dust and noise controls, and protection of ongoing headquarters operations.

- Provide and maintain an acceptable onsite superintendent, quality-control manager, and site safety and health officer whenever construction is in progress.

- Submit design packages, product data, schedules, quality-control records, safety records, certified payrolls, test reports, commissioning records, and as-built information at the frequencies stated in the order.

- Coordinate outages, escorts, Government reviews, and access windows through the channels identified in the order. Government coordination does not relieve the contractor of schedule and notice duties.

- Perform only the work required by the executed order and written modifications. Record potential scope, schedule, or cost effects and promptly present them through the contract-administration process.

# Key incorporated clauses

| Clause | Administration subject |
| --- | --- |
| FAR 52.236-3 | Site investigation and conditions affecting the work |
| FAR 52.236-6 | Superintendence by the contractor |
| FAR 52.236-13 | Accident prevention |
| FAR 52.242-14 | Suspension of work |
| FAR 52.243-4 | Changes |
| FAR 52.249-10 | Default (fixed-price construction) |
| DFARS 252.243-7001 | Pricing of contract modifications |
| DFARS 252.243-7002 | Requests for equitable adjustment |

# Administration contacts

| Contracting Officer | Maj Emma Emmerich, 713th Contracting Squadron (713 CONS) |
| --- | --- |
| Contract Specialist | Nastasha Romanenko, 713 CONS |
| Requiring activity | 713th Civil Engineering Squadron (713 CES) |
| COR transition | Sgt Johnny unavailable on medical leave · 1st Lt Jack “Raiden,” 713 CES, proposed replacement |

COR SURVEILLANCE SUMMARY

Type B · Monthly documented surveillance

This summary assigns the surveillance outcomes and reporting rhythm for the designated COR. It does not alter the contractor's obligations or independently delegate authority. The signed COR designation controls the COR's authority.

# Surveillance objectives and methods

| Performance objective | Method | Minimum frequency | Evidence |
| --- | --- | --- | --- |
| Schedule / phasing | Review schedule and field progress | Weekly; monthly roll-up | Schedule update, daily reports, meeting notes |
| Quality / conformance | Inspection and milestone witness | Weekly and at hold points | Inspection log, test results, deficiency status |
| Safety / occupied facility | Observation and record review | Each visit; weekly review | Safety reports, notices, corrective actions |
| Submittals / Government action | Status and aging review | Weekly | Submittal register, response dates, open actions |
| Labor standards | Payroll review and interviews | Weekly payroll; periodic interview | Certified payrolls, interview records |
| Invoice support | Compare claimed progress with accepted work | Monthly | Payment request, measurements, photographs |
| Access / security | Observe and review incidents | Continuous; monthly roll-up | Roster, access log, incident record |
| Potential changes / claims | Log and refer for CO action | As identified; monthly roll-up | Correspondence and issue log |

# Monthly surveillance report requirement

The COR shall prepare one surveillance report for every calendar month of active performance and upload it to the Surveillance and Performance Module (SPM) no later than the fifth workday of the following month. Send the Contracting Officer a completion notice and immediately elevate any matter that cannot wait for the monthly report.

MONTHLY REPORT CONTENT AND RECORD ROUTE

FA-27-005 · COR working summary

# Required monthly report content

- Reporting month, site visits, surveillance actions, persons contacted, and records reviewed.

- Performance result for each objective: acceptable, needs attention, or unacceptable, with facts supporting the result.

- Deficiencies, contractor corrective actions, due dates, verification status, and any unresolved recurring problem.

- Current schedule status, critical activities, forecast completion, delay notices, mitigation, and known concurrency facts.

- Submittal status and any late Government-furnished information, service, review, access, or decision.

- Safety, security, access, quality-control, testing, and labor-standards observations.

- Invoice and physical-progress support, including inspected work and qualifying materials.

- Potential change, REA, claim, or out-of-scope request identified during the month and the date referred for Contracting Officer action.

- Photographs, meeting records, correspondence, inspection logs, and other evidence relied upon.

- Overall assessment, open risks for the next month, and COR signature and date.

# Record route

| Record | System / recipient | Timing |
| --- | --- | --- |
| Individual surveillance activity | SPM COR file | Promptly after action |
| Monthly surveillance report | SPM; notice to Contracting Officer | By fifth workday after month-end |
| Urgent safety, security, quality, delay, funding, or performance issue | Contracting Officer and COR supervisor | Immediately; do not wait for monthly report |
| Final turnover | Contracting Officer / successor COR | At termination, replacement, or closeout |

Acknowledgement: The designated COR confirms receipt of this surveillance summary through the written COR designation and maintains the official record in JAM/SPM as directed.

| Date | Contracting Officer Maj Emma Emmerich, 713 CONS | Signature /s/ Emma Emmerich |
| --- | --- | --- |
| Date | Designated COR See current written designation | Signature |