DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

# OPERATIONAL REQUEST EMAIL

Office 214 temperature control before wall closeout

| From | Col Roy Campbell, Commander, 713 ABW |
| --- | --- |
| To | 1st Lt Jack 'Raiden,' Campbell Hall COR |
| Sent | 11 August 2027 at 0758 |
| Subject | Office 214 temperature control before wall closeout |

## Message

Jack, the office planned for installation-command work needs reliable independent temperature control during winter operations. Please have Peace Walker add a dedicated cold-climate mini-split while the wall is still open. Coordinate it today so the work does not delay the renovation, and send me confirmation when it is handled.

Roy

The email contains no price, funding citation, Contracting Officer approval, change order, or instruction from Colonel Campbell directly to Peace Walker. Raiden forwarded the request to the contractor at 0817 and asked for a same-day field-work proposal.

## Header verification

| RECORD | RESULT |
| --- | --- |
| Wing email archive | Message and timestamp verified |
| Distribution | Campbell and Raiden only |
| Attachments | None |
| Later contractor contact | No Campbell-to-contractor message identified |