EXERCISE USE ONLY
DEPARTMENT OF THE AIR FORCE
SHADOW MOSES AIR FIELD, ALASKA
BENEFIT AND TECHNICAL ACCEPTANCE RECORD
Campbell Hall Office 214 dedicated mini-split
	Inspected
	18 August 2027 by 713 CES Mechanical Systems

	System
	One cold-climate ductless heat-pump mini-split serving Office 214

	Invoice
	IG-01 / PW-FA27-005-EXW-001 — $32,000

	Condition
	Installed, tested, operational, and retained in Government use


Technical inspection
	CHECK
	RESULT
	EVIDENCE

	Equipment and capacity
	Acceptable
	Cold-climate rated; design load and submittal data verified

	Electrical installation
	Acceptable
	Dedicated circuit, disconnect, labeling, grounding, and test complete

	Mechanical installation
	Acceptable
	Line set, insulation, condensate, penetration seal, and weather seal complete

	Startup and controls
	Acceptable
	Functional test passed; temperature and defrost controls operate

	Government use
	Confirmed
	Office 214 has used the system continuously since 16 August 2027


	FAR 1.602-3(c)(1) FACT: The Government accepted the benefit of an operational, technically acceptable system and continues to use it. This finding supports one ratification condition; it does not by itself authorize payment or establish contracting authority.


Price-analysis record
	ELEMENT
	INVOICE
	GOVERNMENT BENCHMARK
	ANALYSIS

	Equipment
	$13,680
	$14,050
	Localized supplier catalog and freight

	Electrical
	$5,420
	$5,600
	Quantity takeoff and regional labor

	Mechanical
	$3,260
	$3,390
	Quantity takeoff and regional labor

	Field labor
	$8,360
	$8,588
	76 hours × $113 benchmark

	Closeout
	$1,280
	$1,300
	Startup, test, cleanup, turnover

	TOTAL
	$32,000
	$32,928
	Invoice is 2.8% below the evaluated benchmark




PRICE DETERMINATION AND FUNDS RECORD
FAR 1.602-3(c)(4) and (6)
Contracting Officer price determination
I compared the contractor's segregated invoice, supplier purchase records, timecards, local catalog data, regional construction labor, freight, and the Government's independent quantity takeoff. The invoiced total is 2.8 percent below the $32,928 Government benchmark. No duplicate cost, unsupported contingency, or cost already paid under Task Order FA-27-005 was identified. I determine $32,000 fair and reasonable for ratification purposes.
/s/ EMMA EMMERICH
Emma Emmerich
Major, USAF | Contracting Officer, 713 CONS
20 August 2027
Funds availability certification
	TEST
	RECORD
	RESULT

	Purpose
	FY24 Military Construction, Air Force (3300), Project SM-24-001 — Campbell Hall
	Appropriate to the Campbell Hall construction project

	At commitment
	Unobligated balance on 11 August 2027: $418,600
	$32,000 was available

	At ratification
	Unobligated balance reserved on 20 August 2027: $386,600
	$32,000 remains available

	Amount
	Accounting classification 57 3300 24 713 3010 SM-24-001
	Full proposed ratification amount certified


	FUNDS CERTIFICATION: I certify that $32,000 of FY24 Military Construction, Air Force funds was legally available for this project when the commitment occurred and remains available for the proposed ratification. This certification does not obligate funds until the authorized ratifying official approves and the Contracting Officer executes the proper contractual action.


/s/ ROSEMARY MARQUEZ
Rosemary Marquez
Captain, USAF | Certifying Official, 713 CPTS
20 August 2027
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