DEPARTMENT OF THE AIR FORCE

SHADOW MOSES AIR FIELD, ALASKA

PROCUREMENT-PROPRIETY RECORD

Could this purchase have been proper if made by an appropriate Contracting Officer?

| Requirement | Dedicated cold-climate mini-split serving Campbell Hall Office 214 |
| --- | --- |
| Amount | $32,000 firm-fixed-price change value |
| Existing vehicle | SM-MACC-01, Task Order FA-27-005 with Peace Walker Infrastructure Partners, LLC |
| Review standard | FAR 1.602-3(c)(3) and all other applicable limitations |

| PROPRIETY TEST | FACTS | RESULT |
| --- | --- | --- |
| Government purpose | Permanent environmental control for the installation command office and Government equipment; remains with the facility for successor occupants. | Proper Government construction purpose |
| General scope | Same facility, HVAC/electrical trades, renovation period, and performance objective; $32,000 is about 0.12% of the $26.40M task order. | Within modeled general scope of the competed order |
| Contract authority | FAR 52.243-4 permits the Contracting Officer to order in-scope changes; a written funded change could have been negotiated before performance. | Lawful route existed |
| Competition / vehicle | No new facility, acquisition vehicle, or materially different field of competitors would have resulted from this limited in-scope change. | No modeled competition defect |
| Price and funds | IG-04 supports $32,000 as fair and reasonable and confirms appropriate funds then and now. | Supported |
| Prohibited conduct | No gratuity, personal payment, splitting, conflict, or barred source is identified. Campbell's authority failure is addressed through ratification and corrective action. | No other modeled bar |

FAR 1.602-3(c)(3) FINDING: The resulting contract would otherwise have been proper if Maj Emma Emmerich had issued a written, funded change before performance. This finding does not excuse the unauthorized direction or replace ratification.

/s/ EMMA EMMERICH
Emma Emmerich
Major, USAF | Contracting Officer, 713 CONS
21 August 2027

RATIFYING-AUTHORITY RECORD

Current DAF approval matrix applied to $32,000

## Regulatory route

| AUTHORITY | RULE | APPLICATION |
| --- | --- | --- |
| FAR 1.602-3(b)(2)–(3) | Ratification may be delegated under agency procedure, but never below the chief of the contracting office. | DAF uses its approval matrix. |
| DAFFARS 5301.602-3(b)(2) | See MP5301.601(a)(i) and the current ratification approval template. | Both apply to this package. |
| MP5301.601(a)(i), item 4 | Below-SAT unauthorized commitments: COCO; further delegable — No. | $32,000 is below the current $350,000 SAT. |

| Authorized official | Lt Col Helena Dolph Jackson, Commander and COCO, 713th Contracting Squadron |
| --- | --- |
| Delegation | None; approval authority is not further delegable |
| Contracting Officer role | Investigate, determine price, prepare the case summary, recommend payment, and route the package |
| Decision status | Pending complete organization report, legal concurrence, and COCO action in IG-07 |

AUTHORITY FINDING: The proposed ratifying official has authority to enter into the contractual commitment and is the current DAF matrix official for this below-SAT action. Maj Emmerich may recommend ratification but may not approve it by convenience or ordinary bilateral signature.