OFFICE OF THE STAFF JUDGE ADVOCATE

SHADOW MOSES AIR FIELD, ALASKA

MEMORANDUM FOR: Maj Emma Emmerich, Contracting Officer, 713 CONS

FROM: Maj Naomi Hunter, Deputy Staff Judge Advocate, 713 ABW/JA

DATE: 24 August 2027

SUBJECT: Legal concurrence — proposed $32,000 ratification, Campbell Hall Office 214

## Question presented

Whether the $32,000 commitment created when Colonel Roy Campbell directed Peace Walker to install an extra-contractual mini-split may be ratified under FAR 1.602-3 and current DAF procedure.

## Legal analysis

| ISSUE | LEGAL CONCLUSION | SUPPORT |
| --- | --- | --- |
| Authority | Campbell had command authority but no express or implied actual contracting authority. His rank and directive wording created, at most, apparent authority. | FAR 1.602-1; The Portland Mint v. United States |
| Unauthorized commitment | The oral agreement was not binding solely because Campbell lacked authority. | FAR 1.602-3(a); IG-03 |
| Benefit | Government accepted and uses a technically acceptable system. | FAR 1.602-3(c)(1); IG-04 |
| Authority to ratify | The current DAF matrix assigns this below-SAT action to the COCO, without further delegation. | FAR 1.602-3(b); DAFFARS 5301.602-3; MP5301.601(a)(i) |
| Proper purchase | The in-scope facility change could have been lawfully ordered in writing by the CO before performance. | FAR 1.602-3(c)(3); IG-05 |
| Price and funds | $32,000 is fair and reasonable; appropriate funds existed then and remain available. | FAR 1.602-3(c)(4), (6); IG-04 |
| Agency limits | The organization report and complete routing record satisfy the modeled DAF package requirements. | FAR 1.602-3(c)(7); IG-06 and this record |

LEGAL CONCURRENCE: I concur in the Contracting Officer's recommendation to ratify $32,000, provided the COCO approves before the Contracting Officer executes the written contractual and payment action. An ordinary bilateral modification signed before ratification would not cure the unauthorized commitment.

/s/ NAOMI HUNTER
Naomi Hunter
Major, USAF | Deputy Staff Judge Advocate, 713 ABW/JA
24 August 2027

CONTRACTING OFFICER CASE SUMMARY

Recommendation for below-SAT ratification

| Unauthorized commitment | Colonel Campbell's 11 August 2027 direction to Peace Walker |
| --- | --- |
| Amount | $32,000 |
| Contract | SM-MACC-01, Task Order FA-27-005 |
| Recommended decision | Ratify and authorize subsequent written contractual and payment action |

## Case summary

Peace Walker installed a dedicated cold-climate mini-split after Colonel Campbell directed the work at the active project. Campbell lacked contracting authority; Maj Emma Emmerich did not authorize or know of the work before performance. Peace Walker's good-faith reliance on Campbell's rank and command position explains its conduct but does not bind the Government. The Government has retained and uses the technically acceptable system.

## FAR 1.602-3(c) recommendation record

| CONDITION | EVIDENCE | CO FINDING |
| --- | --- | --- |
| Government benefit | IG-04 technical acceptance and use record | Satisfied |
| Ratifying-official authority | IG-05 current DAF matrix application | COCO has authority |
| Otherwise proper purchase | IG-02 and IG-05 scope / vehicle analysis | Satisfied |
| Fair and reasonable price | IG-04 independent benchmark and CO determination | $32,000 fair and reasonable |
| CO recommendation / legal | This summary and signed 713 ABW/JA concurrence | Satisfied |
| Funds then and now | IG-04 713 CPTS certification | Satisfied |
| Other agency limitations | IG-03, IG-06, and routing checklist | Satisfied |

## Recommendation

I recommend that the COCO ratify the $32,000 unauthorized commitment. After approval, I will execute the appropriate written contract action citing the ratification, scope, price, funds, and complete-adjustment terms; process the supported contractor invoice; update the contract and finance records; and retain the corrective-action package. No payment or ordinary modification will precede the COCO decision.

/s/ EMMA EMMERICH
Emma Emmerich
Major, USAF | Contracting Officer, 713 CONS
24 August 2027

RATIFICATION APPROVAL ROUTING RECORD

Decision authority: 713 CONS COCO | $32,000 below SAT

| PACKAGE ITEM | RECORD | STATUS |
| --- | --- | --- |
| Contractor invoice and basis | IG-01 | Complete |
| Original scope / extra-work evidence | IG-02 | Complete |
| CO investigation and individual statements | IG-03 | Complete |
| Benefit, technical acceptance, price, and funds | IG-04 | Complete |
| Otherwise-proper purchase and approval authority | IG-05 | Complete |
| Organization circumstances, corrective, and disciplinary action | IG-06 | Complete |
| Legal concurrence and CO recommendation | IG-07 pages 1–2 | Complete |

## Coordination

| FUNCTION | NAME / POSITION | ACTION / DATE |
| --- | --- | --- |
| Requiring organization | Lt Col Mei Ling, 713 CES/CC | /s/ Mei Ling — 23 Aug 2027 |
| Funds certification | Capt Rosemary Marquez, 713 CPTS | /s/ Rosemary Marquez — 20 Aug 2027 |
| Legal review | Maj Naomi Hunter, 713 ABW/JA | /s/ Naomi Hunter — 24 Aug 2027 |
| CO recommendation | Maj Emma Emmerich, 713 CONS | /s/ Emma Emmerich — 24 Aug 2027 |

## COCO decision

| ☐ APPROVE RATIFICATION AT $32,000 | ☐ DISAPPROVE — ATTACH LEGAL BASIS |
| --- | --- |
| Signature: ______________________________ Lt Col Helena Dolph Jackson Commander and COCO, 713 CONS | Date: __________________ Approval is not further delegable. |

FACILITATOR CONTROL: Leave the decision block unsigned until trainees select and justify a response. On the intended complete record, the strong response results in COCO approval, followed by the Contracting Officer's written contractual and payment action.