DIAMOND DOGS CIVIL WORKS, LLC

SHADOW MOSES AIR FIELD, ALASKA

FIRM-FIXED-PRICE REDUCTION PROPOSAL

Temporary use of 713 LRS REX-45 | FA-27-008

| Proposal | DD-CMOD-27-014 |
| --- | --- |
| Submitted / signed | 24 August 2027 / 0835 Alaska time - /s/ Dana Rourke, Program Manager |
| Validity | Through 25 August 2027 / 1200 Alaska time |
| Requested property term | 25 August-3 September 2027; maximum 80 operating hours |
| Pricing basis | Firm-fixed-price credit conditioned on written bilateral modification |

# Price adjustment

| Element | Basis | Adjustment |
| --- | --- | --- |
| Avoided replacement-equipment allowance | Ten-day high-capacity rental, mobilization, and return logistics removed from contractor price | -$74,500 |
| Contractor support retained | Operator, signal personnel, fuel, daily checks, issue/return support, and records | +$6,500 |
| NET TASK-ORDER REDUCTION | Firm-fixed-price credit | -$68,000 |

TASK-ORDER VALUE: Current awarded value $8,615,000 - proposed reduction $68,000 = proposed revised value $8,547,000.

# Conditions of the offer

| Condition | Offeror position |
| --- | --- |
| Delivery / return | Government stages the REX-45 at Building 100 by 0700 on 25 August; Diamond Dogs returns it to the LRS yard by 1800 on 3 September. |
| Operation | Diamond Dogs furnishes the operator, signal personnel, fuel, daily checks, and work-zone controls. |
| Condition record | The parties perform joint issue and return inspections and record hours, fuel, photographs, and discrepancies. |
| Property terms | Accountability, authorized use, maintenance, loss reporting, risk, and liability will be stated in the written modification. |
| Schedule | No schedule extension is included in this offer if the property is staged as proposed. |