EXERCISE USE ONLY
DIAMOND DOGS CIVIL WORKS, LLC
SHADOW MOSES AIR FIELD, ALASKA
FIRM-FIXED-PRICE REDUCTION PROPOSAL
Temporary use of 713 LRS REX-45 | FA-27-008
	Proposal
	DD-CMOD-27-014

	Submitted / signed
	24 August 2027 / 0835 Alaska time - /s/ Dana Rourke, Program Manager

	Validity
	Through 25 August 2027 / 1200 Alaska time

	Requested property term
	25 August-3 September 2027; maximum 80 operating hours

	Pricing basis
	Firm-fixed-price credit conditioned on written bilateral modification


Price adjustment
	Element
	Basis
	Adjustment

	Avoided replacement-equipment allowance
	Ten-day high-capacity rental, mobilization, and return logistics removed from contractor price
	-$74,500

	Contractor support retained
	Operator, signal personnel, fuel, daily checks, issue/return support, and records
	+$6,500

	NET TASK-ORDER REDUCTION
	Firm-fixed-price credit
	-$68,000


 
	TASK-ORDER VALUE: Current awarded value $8,615,000 - proposed reduction $68,000 = proposed revised value $8,547,000.


Conditions of the offer
	Condition
	Offeror position

	Delivery / return
	Government stages the REX-45 at Building 100 by 0700 on 25 August; Diamond Dogs returns it to the LRS yard by 1800 on 3 September.

	Operation
	Diamond Dogs furnishes the operator, signal personnel, fuel, daily checks, and work-zone controls.

	Condition record
	The parties perform joint issue and return inspections and record hours, fuel, photographs, and discrepancies.

	Property terms
	Accountability, authorized use, maintenance, loss reporting, risk, and liability will be stated in the written modification.

	Schedule
	No schedule extension is included in this offer if the property is staged as proposed.
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