DIAMOND DOGS CIVIL WORKS, LLC

SHADOW MOSES AIR FIELD, ALASKA

COMMAND POST EARLY-SITEWORK SCHEDULE

FA-27-008 | Update through 24 August 2027

| Notice to proceed | 16 August 2027 |
| --- | --- |
| Contract turnover | 29 September 2028; Government requirement 15 October 2028 |
| Current package | EWP-01 - boulder source acceptance, temporary staging, and full-scale mockup only |
| Equipment event | Rented telehandler hydraulic-pump failure reported 24 August 2027 |

EARLY-WORK LIMIT: Government release of EWP-01 on 23 August authorizes only source inspection, preparation of the temporary stockpile area, and the full-scale boulder mockup. Final barrier foundations and placement remain subject to later accepted design packages.

# Near-term and baseline activities

| Activity | Date / period | Status | Dependency / note |
| --- | --- | --- | --- |
| Award and notice to proceed | 16 Aug 2027 | ACTUAL | Baseline, field verification, and submittal controls begin |
| Field verification and boulder inventory | 16-22 Aug 2027 | ACTUAL | Supports EWP-01 and site-security concept validation |
| EWP-01 accepted for limited release | 23 Aug 2027 | ACTUAL | Temporary staging and mockup only; no final barrier placement |
| Rental telehandler failure | 24 Aug 2027 | ACTUAL | High-capacity lifting source unavailable during mobilization |
| Boulder source acceptance, staging, and mockup | 25 Aug-3 Sep 2027 | AT RISK | Ten-day lifting window; mockup record feeds design review |
| Mockup review and model update | 4-8 Sep 2027 | PLANNED | Close comments before the 35-percent design package |
| 35-percent design review | 22 Sep 2027 | MILESTONE | Confirms site, floor, systems, and long-lead basis |
| Final barrier foundations and placement | 3 Jun-9 Aug 2028 | BASELINE | Requires accepted final civil/security design and coordinated site access |
| Commissioning, training, and closeout | 12 Aug-29 Sep 2028 | BASELINE | Offeror turnover 16 days before Government required date |

SCHEDULE EFFECT CLAIMED BY CONTRACTOR: Diamond Dogs states that losing the 25 August-3 September lifting window would compress mockup review and the 35-percent design basis. This update identifies the asserted schedule pressure; it does not select an equipment source or approve a contract change.

| Signed | Name / position | Date |
| --- | --- | --- |
| /s/ Dana Rourke | Dana Rourke Program Manager, Diamond Dogs Civil Works, LLC | 24 Aug 2027 |