EXERCISE USE ONLY
OUTER HEAVEN BUILDERS, LLC
SHADOW MOSES AIR FIELD, ALASKA
TO: Maj Helena Dolph Jackson, Contracting Officer, 713 CONS
FROM: Robin Hale, Project Manager, Outer Heaven Builders, LLC
DATE: 22 September 2027
SUBJECT: Transmittal - request for eleven-calendar-day weather extension
REFERENCE: SM-SABER-01 Task Order 27-064, Mother Base Community Support Center Roof Replacement
Prime-contractor transmittal
Outer Heaven Builders, LLC forwards the attached 20 September request from its roofing subcontractor, Diamond Dogs Roofing, LLC. Outer Heaven adopts the request as its own and asks the Contracting Officer to extend the task-order completion date by eleven calendar days. This transmittal does not create contractual privity between the Government and the subcontractor.
The request seeks time only and no price adjustment. Outer Heaven states that the eleven listed rain dates prevented safe roofing work and affected the planned roof dry-in sequence. The task order incorporates FAR 52.249-10, Default (Fixed-Price Construction), and FAR 52.211-12, Liquidated Damages - Construction; the complete incorporated clauses control.
Task-order time baseline
	Record
	Task-order value

	Award / value
	10 Aug 2027 / $5,180,000 firm-fixed price

	Notice to proceed
	16 Aug 2027

	Performance period
	75 calendar days after notice to proceed

	Original completion
	30 Oct 2027

	Requested extension
	11 calendar days

	Requested completion
	10 Nov 2027

	Liquidated-damages rate
	$8,500 for each calendar day of unexcused delay after 30 Oct 2027


	REQUESTED ACTION: Determine whether the eleven dates qualify for a noncompensable time extension. Outer Heaven asks that the original completion date remain unchanged unless and until the Contracting Officer executes a written modification.


	Signed
	Name / position
	Date

	/s/ Robin Hale
	Robin Hale
Project Manager, Outer Heaven Builders, LLC
	22 Sep 2027




DIAMOND DOGS ROOFING, LLC
SHADOW MOSES AIR FIELD, ALASKA
SUBCONTRACTOR WEATHER-DELAY REQUEST
Submitted to Outer Heaven Builders, LLC | Community Support Center roof replacement
	Request date
	20 September 2027

	Reporting period
	1-16 September 2027

	Requested relief
	Eleven-calendar-day, noncompensable extension

	Prime contract
	SM-SABER-01 Task Order 27-064; original completion 30 October 2027

	Supporting record
	Outer Heaven daily reports DR-09-01 through DR-09-16 and selected photographs


Claimed interruption dates
	Date
	Scheduled roofing activity
	Daily-report statement

	1 Sep
	Existing membrane removal
	Full roofing shift stopped; wet surface and standing water

	2 Sep
	Insulation removal / deck exposure
	Full roofing shift stopped; wet deck could not be exposed

	3 Sep
	Deck preparation
	Full roofing shift stopped; water remained in low areas

	7 Sep
	Vapor-retarder placement
	Full roofing shift stopped; substrate remained damp

	8 Sep
	Insulation placement
	Full roofing shift stopped; materials kept covered

	9 Sep
	Membrane installation
	Full roofing shift stopped; surface water continued

	10 Sep
	Membrane installation
	Full roofing shift stopped; adhesion conditions not met

	13 Sep
	Membrane seams / flashing
	Full roofing shift stopped; rain and wet work surface

	14 Sep
	Perimeter and curb flashing
	Full roofing shift stopped; standing water at drains

	15 Sep
	Roof dry-in progression
	Full roofing shift stopped; work area remained wet

	16 Sep
	Roof dry-in progression
	Full roofing shift stopped; rain during planned shift


	SUBCONTRACTOR POSITION: Each listed date prevented a full planned roofing shift. Diamond Dogs Roofing therefore requests one calendar day for each affected date and asks Outer Heaven Builders to obtain an eleven-calendar-day extension from the Government.


/s/ Evan Brooks  |  Project Manager, Diamond Dogs Roofing, LLC  |  20 Sep 2027
Record note: This subcontractor request is attached to and adopted by Outer Heaven's transmittal on page 1.





