713TH CIVIL ENGINEER SQUADRON

SHADOW MOSES AIR FIELD, ALASKA

HISTORICAL AND ANTICIPATED ADVERSE-WEATHER BASELINE

Community Support Center Roof Replacement | Task-order schedule-planning record

| Record | 713 CES/WP-27-041 |
| --- | --- |
| Issued | 9 August 2027 |
| Weather basis | Shadow Moses installation observations, 2017-2026 |
| Contract use | SM-SABER-01 Task Order 27-064 schedule administration |

# Accepted planning baseline

The task-order planning record uses the following monthly allowances for roofing days expected to be unavailable because of precipitation or persistent wet-surface conditions. A qualifying day is counted once, even when more than one weather condition occurs.

| Month | Anticipated roofing weather-loss days | Ten-year average monthly precipitation |
| --- | --- | --- |
| August | 10 | 5.10 in |
| September | 12 | 6.80 in |
| October | 14 | 7.45 in |
| November | 16 | 8.10 in |

SEPTEMBER BASELINE: The accepted planning record assigns 12 anticipated adverse-weather days to September. Compare the dates covered by a September extension request with the contemporaneous site-weather observations.

Counting criterion: precipitation of at least 0.10 inch during the roofing shift, or documented wet-surface conditions that prevented roofing for more than four hours. The criterion is applied consistently to the planning record and the actual observation log.

/s/ Lena Ortiz  |  Installation Weather Planning Analyst, 713 CES  |  9 Aug 2027

Record note: Exercise-specific Government planning record furnished from the Task Order 27-064 contract file.