EXERCISE USE ONLY
713TH CIVIL ENGINEER SQUADRON
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HISTORICAL AND ANTICIPATED ADVERSE-WEATHER BASELINE
Community Support Center Roof Replacement | Task-order schedule-planning record
	Record
	713 CES/WP-27-041

	Issued
	9 August 2027

	Weather basis
	Shadow Moses installation observations, 2017-2026

	Contract use
	SM-SABER-01 Task Order 27-064 schedule administration


Accepted planning baseline
The task-order planning record uses the following monthly allowances for roofing days expected to be unavailable because of precipitation or persistent wet-surface conditions. A qualifying day is counted once, even when more than one weather condition occurs.
	Month
	Anticipated roofing weather-loss days
	Ten-year average monthly precipitation

	August
	10
	5.10 in

	September
	12
	6.80 in

	October
	14
	7.45 in

	November
	16
	8.10 in


	SEPTEMBER BASELINE: The accepted planning record assigns 12 anticipated adverse-weather days to September. Compare the dates covered by a September extension request with the contemporaneous site-weather observations.


Counting criterion: precipitation of at least 0.10 inch during the roofing shift, or documented wet-surface conditions that prevented roofing for more than four hours. The criterion is applied consistently to the planning record and the actual observation log.
/s/ Lena Ortiz  |  Installation Weather Planning Analyst, 713 CES  |  9 Aug 2027
Record note: Exercise-specific Government planning record furnished from the Task Order 27-064 contract file.





