713TH OPERATIONS SUPPORT SQUADRON - WEATHER FLIGHT

SHADOW MOSES AIR FIELD, ALASKA

ACTUAL SITE WEATHER OBSERVATION LOG

Shadow Moses Air Field | Community Support Center | 1-20 September 2027

| Station / record | SMO-WX-01 / September roofing observation extract |
| --- | --- |
| Observation window | 0000-1800 local daily; conditions confirmed against contractor daily reports |
| Counting criterion | At least 0.10 in precipitation during shift, or wet-surface restriction over four hours |

# Daily observations

| Date | Precip. (in) | Roofing-shift observation | Qualifying day | Matches claimed date |
| --- | --- | --- | --- | --- |
| 1 Sep | 0.44 | Rain; standing water; roofing stopped | Yes | Yes |
| 2 Sep | 0.38 | Rain; wet deck; roofing stopped | Yes | Yes |
| 3 Sep | 0.26 | Rain; water in low areas; roofing stopped | Yes | Yes |
| 4 Sep | 0.02 | Trace after shift; no roofing stoppage | No | No |
| 5 Sep | 0.00 | Dry; roofing proceeded | No | No |
| 6 Sep | 0.04 | Light rain; serviceable by 0800 | No | No |
| 7 Sep | 0.51 | Rain; substrate remained wet; roofing stopped | Yes | Yes |
| 8 Sep | 0.36 | Rain; materials remained covered | Yes | Yes |
| 9 Sep | 0.42 | Rain; surface water; roofing stopped | Yes | Yes |
| 10 Sep | 0.31 | Rain; adhesion conditions not met | Yes | Yes |
| 11 Sep | 0.00 | Dry; roofing proceeded | No | No |
| 12 Sep | 0.06 | Light rain; no full-shift restriction | No | No |
| 13 Sep | 0.48 | Rain; wet work surface; roofing stopped | Yes | Yes |
| 14 Sep | 0.39 | Rain; standing water at drains | Yes | Yes |
| 15 Sep | 0.33 | Rain; work area remained wet | Yes | Yes |
| 16 Sep | 0.29 | Rain during shift; roofing stopped | Yes | Yes |
| 17 Sep | 0.00 | Dry; roofing proceeded | No | No |
| 18 Sep | 0.08 | Light rain; no full-shift restriction | No | No |
| 19 Sep | 0.00 | Dry; roofing proceeded | No | No |
| 20 Sep | 0.00 | Dry; roofing proceeded | No | No |

OBSERVATION SUMMARY: Qualifying weather-loss days through 20 September: 11. The qualifying dates are the same eleven dates identified in the contractor's request. L-03 lists the accepted September planning baseline.

/s/ Capt Tessa Mallory  |  Weather Flight Commander, 713 OSS  |  21 Sep 2027

Record note: Exercise-specific observation log; precipitation and field-condition entries are fictional.