713TH LOGISTICS READINESS SQUADRON

SHADOW MOSES AIR FIELD, ALASKA

EAST CARGO APRON AVAILABILITY SCHEDULE

Port Operations control record - 10 June through 9 July 2027

| Area | East Cargo Apron shown on N-03 |
| --- | --- |
| Control office | Deployment and Distribution Flight, 713th Logistics Readiness Squadron (713 LRS) |
| Schedule status | Approved internal operating schedule; current as of 24 May 2027 |
| Prepared by | SSgt Olga Gurlukovich, Port Operations |

# Operating windows

| Dates | Availability | Controlling activity / condition |
| --- | --- | --- |
| 10-13 Jun 2027 | AVAILABLE | Contractor staging and laydown may be coordinated through ordinary daily Port Operations controls. |
| 14-25 Jun 2027 | UNAVAILABLE | Summer sealift reservation. Apron must remain clear for cargo marshaling, material handling, berth safety, and Government equipment. |
| 26-30 Jun 2027 | AVAILABLE | Contractor staging and laydown may resume after Port Operations releases the area. |
| 1-9 Jul 2027 | AVAILABLE | Ordinary daily coordination applies; mission or emergency cargo retains priority. |

# Daily control conditions

- Provide a 24-hour look-ahead for planned crane placement, deliveries, laydown footprint, and equipment movement.

- Receive same-day Port Operations release before occupying the apron; weather, berth safety, mission cargo, or an emergency may temporarily restrict use.

- Keep marked access lanes, fire protection routes, warehouse doors, and the pier emergency edge clear at all times.

- Only the 713 LRS controlling office may revise these dates. Coordination with another Government office does not independently reserve the apron.

SCHEDULE EFFECT: The firm 14-25 June closure affects crane reservations, staging, sequencing, schedule, and price during the contemplated initial mobilization period.

/s/ DIANE AMES, Capt, USAF
Deployment and Distribution Flight Commander, 713 LRS
Approved 24 May 2027